## Slide 1: Presentation
CONSTRUCTION, PLANNING & MANAGEMENT
PC-1
DUALIZATION OF LEHTRAR ROAD FROM
TRAMARI CHOWK TO P.I.N.S.TECH, ISLAMABAD
PRESENTED BY GROUP 2

## Slide 2
PC-I PROFORMA FOR
DUALIZATION OF LEHTRAR ROAD FROM
TRAMARI CHOWK TO P.I.N.S.TECH, ISLAMABAD. (REVISED)
Cost Rs.1,265.128 Million
File No.CDA-54(263)-Stats/2006
PC-I No1210-82-2010
E:\D.D[E] Docmnts\PINSTECH-Lehtrar Road\Final P&E Revised Tramri.doc

## Slide 3: DESCRIPTION
Lehtrar road is one of the main links which connects Rawalpindi with Azad Kashmir and serves the sub-urban areas along both sides of the road. This road also connects Islamabad to most of the adjoining areas of Capital Territory and very important Government offices such as P.I.N.S.TECH., P.A.E.C office Nilor etc. The traffic on this single road had increased due to rapid development in its surroundings. As a result, the existing 18’-0” wide road had become inadequate to accommodate the traffic load and volume of traffic. The CDA, on the direction of Federal Government, undertook the dualization of Lehtrar road from Tramari Chowk to P.I.N.S.TECH (08 KM Road) including the widening of the existing road.
- . The land within the right of way (150 feet) has already been acquired and there is no major encroachment within the entire length of the proposed road, however, some moveable minor encroachments are there which will be removed during execution

## Slide 4: OBJECTIVES
It is informed that the original PC-I for the Project was considered in a CDA-DWP meeting held on 27th Oct,2007, costing Rs. 581.049 Million and following decision was taken:
“The scheme was approved in principle subject to verification of quantities and cost by Transport & Communication (T&C) Section
and Physical Planning & Housing (PP&H) Section and inclusion of cost of service Roads, where required.”(Annexed at Annexure-A)”

## Slide 5
Now, due to the reasons detailed below,
the PC-I has to be revised to seek approval of the CDA-DWP forum. It is further informed here that before placing the revised scheme to the CDA-DWP, the draft revised scheme (earlier estimated around Rs.1,482.581 million), as per prevailing procedure, was placed before the CDA’s Technical Committee in its meeting held on 30-08-2010. The meeting was chaired by the Chairman-CDA and attended by the Member (Engineering/ P&D),CDA, F.A/Member, CDA, D.G(Works),CDA and concerned Directors. A detailed multimedia presentation giving progress of the project, on-ground issues and reasons/ justification leading to the revision of the PC-I were given to the participants by the Project Director. After detailed deliberation, the Committee decided that the PC-I should be further improved/updated by adding all the shortcomings and the outcome of the various site visits which led to the increase in scope of work and cost of the project. The Project Director was directed to highlight the on-going difficulties like issues of graveyards, right of way, shifting of services, mosque and street lighting in the improved PC-I to have better understanding of the reasons behind the manifold increase in cost and changes which had to be made in approved scope of work. (Copy of decision of this

## Slide 6: NEEDS
The approved PC-I was estimated on NHA CSR 2005.
ii) The NIT was approved on NHA CSR 2008.
iii) The project was awarded at 26.73% premium on NHA CSR 2008 and 112.73% on
MES schedule 2000.
iv) Cost estimate for services and utilities was taken at only Rs.16.2 million, whereas, the actual re-location cost is now around Rs.50.838 million which is almost 314% more than the estimated/approved cost. (The Authority did manage to save Rs.51.3 million on account of relocation of NTC and SNGPL).
v) The project was tendered on Design which was later changed by the Competent Authority.

## Slide 7
1. | Name of the Project | Dualization of from Tramari Chowk to P.I.N.S.TECH, Islamabad.(Revised PC-I)
2. | Location | - Lehtrar Road. . (Map attached).
3. | Authorities responsible for: | 
 | Sponsoring | - Capital Development Authority
 | Execution | -Capital Development Authority
 | Operation and maintenance | -Capital Development Authority
 | Concerned Federal Ministry | -Cabinet Division, Government of .
4. | Plan Provision | -The project is being executed through CDA’s resources. Funds amounting to Rs.760.000 Million are available in Year 2010-11.
GOVERNMENT OF PAKISTAN
PLANNING COMMISSION
(INFRASTRUCTURE SECTORS)
File No.CDA-54(263)-Stats/2006
PC-I No1210-82-2010

## Slide 8
6 | Description, justification, technical parameters and technology transfer aspects (enclose feasibility study for projects costing Rs.300 million and above: i) Length of road = 8.0 km ii) Design & Specifications = The standard specifications of National Highway Authority for construction of roads is being followed. iii) Design Speed = Traffic speed shall be 80 km/hr. iv) Pavement Design = Sub base (Aggregate) = 0’-10’’ Base Course = 1’-0’’ Asphalt wearing course = 0-6”

## Slide 9
7- Capital Cost Estimates. |  |  | (Rs. In Million)
S# | Items of work | Approved Cost | Revised Cost
1. | Sub Head-I Road Work. | 269.304 | 523.80
2. | Sub Head-II Rehabilitation of existing carriageway | 40.323 | 115.851
3. | Sub Head-III Drainage/Kerb stones. | 60.168 | 209.386
4. | Sub Head-IV Protection work. | 51.808 | 40.269
5. | Sub Head-V Signage Work | 8.880 | 26.183
6. | Sub Head-V Bridge/Culvert. | 42.099 | 150.00
7. | E&M Works | 21.000 | 21.00
8. | Soft landscaping (L/S) | 4.521 | 4.521
9. | Protected U-Turns, at grade connections with Approach Roads | - | 43.633

## Slide 10
 |  | BASE COST | 498.103 | 1134.643
10 |  | Shifting of services (PTCL, SNGPL, IESCO etc) | 13.00 | 50.838
11 |  | I.E.S.C.O Charges. | 3.200 | 
12. |  | Contingencies @ 3% | 14.943 | 34.039
13. |  | Departmental Charges @ 6.5% of base cost | 32.377 | -
14. | Escalation charges as per contract | 19.426 | 31.996 | -
15. | Shifting of 01 No. Mosque at Alipur. | - | 5.000 | 
16. | Project Director Cost and allied charges | - | 8.612 | 
 | Grand Total | 581.049 | 1,265.128 | 

## Slide 11
1. | Salaries of staff @ 25% of Rs.26.194 million | 6.549
2. | Consumable Store @ 10% of Rs.26.194 million | 2.619
3. | Work through Contract @ 65% of Rs.26.194 million | 17.026
 | Total | 26.194
8. | Annual operating and maintenance cost after completion of the project | 
9 | Demand and supply analysis | 
10. | Financial plan and mode of financing | N-A
11. | Project benefits and analysis | N-A
i. | Financial | N-A
ii. | Economic | N-A
iii. | Social benefits with indicators | The Project would greatly benefit new development opportunities and bring positive socio economic changes.
iv. | Employment generation (direct and indirect) | N-A
v. | Environmental impact | The project will be helpful in betterment of air pollution and is likely to cause positive environment impact since the site is already developed and dualization of road would not create any adverse impacts on human life.

## Slide 12
vi. | Impact of delays on project cost and viability | Delays may increase project cost, however, no delay on account of funds is expected.
12. | a) Implementation Schedule | 18 months. up to Dec.2010
12(b | Implementation Schedule | - Further 04 months from the date of start of work at site.
13 | Management structure and manpower requirements | -NA-
14 | Additional projects/decisions required Indicate additional projects / decisions required to optimize the investment being undertaken on the project. | -NA-
15 | Certificate The name designation and phone # of the officer responsible for preparing and checking be provided. It may also be confirmed that PC-I has been prepared as per instructions for the preparation of PC-I for social sector projects. | yes

## Slide 13
ANNUAL MAINTENANCE COST
1. | 2 % Road work of Rs.1,068.856 million | 21.377
2. | 3.5% Civil Works of Rs.40.269 million | 1.409
3. | 13% E&M Works of Rs.21.000 Million | 2.730
4. | 15% Soft landscaping of Rs.4.521 million | 0.678
 | Total | 26.194
Rs. in million

## Slide 14
MODE OF EXPENDITURE
Rs. in million
1. | Salaries of staff @ 25% of Rs. 26.194 million | 6.549
2. | Consumable Store @ 10% of Rs. 26.194 million | 2.619
3. | Work through Contract @ 65% of Rs. 26.194 million | 17.026
 | Total | 26.194